## Summery
SOFTWARE TEST REPORT(STR)
Lunch Command Processing (LCP)
Sl | Contents | Revision | Date of Revision | Auther | Remarks
1 | Intial Report Prepared | Initial ver | 2025-09-22 | T Srikanth
| Module | Passed | Failed | Total | Pass%
| Login | 23 | 0 | 23 | 100%
| DG | 10 | 0 | 10 | 100%
| UPS | 11 | 0 | 11 | 100%
| Switch | 10 | 0 | 10 | 100%
| Radio | 9 | 0 | 9 | 100%
| Dashboard | 10 | 0 | 10 | 100%
| Tabular Report | 9 | 0 | 9 | 100%
| LineGraph | 10 | 0 | 10 | 100%
| Archive Management | 10 | 0 | 10 | 100%
| User Management | 11 | 0 | 11 | 100%
| Sub-SystemStatus | 26 | 0 | 26 | 100%
| Total | 139 | 0 | 139

## Login
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
Login_01 | Login | Verify that the 'User Name' input field is present. | Srikanth | 2025-09-16 | when every login clear credentials in the fields. | None | Enter valid username and password, click Login Button. | Username: Icomm Password: Icomm@123 Login successful, Opem Main Window. | The layout should be aligned, text readable, and elements properly spaced. | NA | Pass | Test executed successfully without any issues.
Login_02 | Login | Verify that the 'User Password' input field is present. | Srikanth | 2025-09-16 | Login page must be accessible from the application. | None | Enter incorrect username or password, click Login Button. | Error message: Invalid username or password. | The heading should be clearly visible. | NA | Pass | Test executed successfully without any issues.
Login_03 | Login | Verify that the password field masks the entered characters. | Srikanth | 2025-09-16 | User must not have exceeded the maximum login attempts. | None | Leave username or password empty, click Login Button. | Error message: Invalid username or password. | Both sections should be properly displayed. | NA | Pass | Test executed successfully without any issues.
Login_04 | Login | Verify that both fields accept input. | Srikanth | 2025-09-16 | User must enter the credentials. | None | None( password field empty) | Error message: Invalid username or password. | Clicking on 'Exit' should close the application. | NA | Pass | Test executed successfully without any issues.
Login_05 | Login | Verify that an error message is displayed when either field is empty. | Srikanth | 2025-09-16 | User can enter any character type name.. | None | None(`User Name field empty) | Error message: Invalid username or password. | The logo should be visible and properly aligned. | NA | Pass | Test executed successfully without any issues.
Login_06 | Login | Verify that the 'User Name' field does not accept special characters. | Srikanth | 2025-09-16 | User Must click the Login button. | None | Click Login without entering any data | Error message: Invalid username or password. | The input field should be available for user entry. | NA | Pass | Test executed successfully without any issues.
Login_07 | Login | Verify that the 'Login' button is displayed and enabled. | Srikanth | 2025-09-16 | User Must selcet Device. | None | Enter special characters in the username field, enter a valid password, click Login Button. | Error message: Invalid username or password. | The password input field should be available for user entry. | NA | Pass | Test executed successfully without any issues.
Login_08 | Login | Verify that clicking 'Login' with empty credentials shows an error message. | Srikanth | 2025-09-16 | Remember Me checkbox by Default Un-Checked. | None | Enter in the username field and any password, click Login | Error message: Invalid username or password. | Password should be displayed as asterisks or dots. | NA | Pass | Test executed successfully without any issues.
Login_09 | Login | Verify that clicking 'Login' with an incorrect username/password shows an error message. | Srikanth | 2025-09-16 | Create Exercise checkbox by Default Un-Checked. | None | when click on show -hide Icon password vissible. | it is working fine. | Users should be able to type in both fields. | NA | Pass | Test executed successfully without any issues.
Login_10 | Login | Verify that the 'Forgot Password' link is present and clickable. | Srikanth | 2025-09-16 | by default UserName and Password is Empty. | None | Enter password and check if it's displayed as dots or asterisks | None | The system should show an appropriate error message. | NA | Pass | Test executed successfully without any issues.
Login_11 | Login | Verify that clicking 'Forgot Password' redirects to the password recovery page. | Srikanth | 2025-09-16 | Hide the password by default showed like dots. | None | None | None | The system should restrict invalid characters. | NA | Pass | Test executed successfully without any issues.
Login_12 | Login | Verify that the 'Go Back to Login' link is present and clickable. | Srikanth | 2025-09-16 | None | None | Click on 'Forgot Password' | Reset Password is working as expected . | The button should not be visible and enabled when fields are filled. | NA | Pass | Login button is not disable and Enable
Login_13 | Login | Verify that clicking 'Go Back to Login' link redirects to the normal position. | Srikanth | 2025-09-16 | None | None | Enter the correct password but with different case variations, click Login | Error message: Please Enter Valid Username and Password. | The system should prompt the user to enter credentials. | NA | Pass | Test executed successfully without any issues.
Login_14 | Login | Verify that clicking 'Login' with correct credentials redirects to the device selection window | Srikanth | 2025-09-16 | None | None | Enter incorrect credentials multiple times | User Does not Exits, Invalid username or password. | A 'Invalid credentials' message should be displayed. | NA | Pass | Test executed successfully without any issues.
Login_15 | Login | to verify select the device in the selection window and we have two options select and cancel to choose 'select' option it is redirect to Main window. | Srikanth | 2025-09-16 | None | None | Attempt login when the system is under maintenance | None | The user should be logged in and redirected. | NA | Pass | Test executed successfully without any issues.
Login_16 | Login | Verify that SQL injection is not possible in the username/password fields. | Srikanth | 2025-09-16 | None | None | Log in with valid credentials | Open Main window. | The system should navigate to the password reset screen. | NA | Pass | Test executed successfully without any issues.
Login_17 | Login | Verify that clicking the 'Exit' button closes the application securely. | Srikanth | 2025-09-16 | None | None | Click on 'Select Device' | Open SeclectionDevice Window. | The link should be visible and accessible. | NA | Pass | Test executed successfully without any issues.
Login_18 | Login | verify the Show -hide password when click on button show password only. | Srikanth | 2025-09-16 | None | None | Checked on Remember Me | Is Checked Save the password Untill Uncheck. | A device selection dialog should appear. | NA | Pass | Test executed successfully without any issues.
Login_19 | Login | Verify that the 'Remember Me' option is used to avoid entering the same user credentials every time,using checkbox. | Srikanth | 2025-09-16 | None | None | Checked on Create Execrsice | Is Checked open Execrsice window. | The system should prompt the user to select a device. | NA | Pass | Test executed successfully without any issues.
Login_20 | Login | Verify that the 'CreateExcersice' option is used to who is login the Application and purpose of login Saved using checkbox | Srikanth | 2025-09-16 | None | None | In Excersice Written user Information Click on Save Button. | Data is Saved Succefully Saved, The Record is Saved in DB. | The application should close without errors. | NA | Pass | Test executed successfully without any issues.
Login_21 | Login | None | Srikanth | 2025-09-16 | None | None | In the popup message 'Data is Saved Succefully Saved' then Click on OK button. | The Execrsice window is Closed. | show-hide password clicked on button working fine. | NA | Pass | Test executed successfully without any issues.
Login_22 | Login | None | Srikanth | 2025-09-16 | None | None | In Excersice window empty details try to Save Click on SaveButton. | Error message:Please enter Exercise Type | None | NA | Pass | Test executed successfully without any issues.
Login_23 | Login | None | Srikanth | 2025-09-16 | None | None | In Excersicetype is length is lessthen 4 chars | Error message: Enter atleast 4 charecters | None | NA | Pass | Test executed successfully without any issues.

## DG
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
DG_001 | DieselGenerator | Verify 'Mains Parameters' values are displayed correctly | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Navigate to the application and check the values under 'Mains Parameters' | User can see the Live data is here | Values should match expected generator readings | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_002 | DieselGenerator | Verify 'Engine Group' values are displayed correctly | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Check values under 'Engine Group' | User can see the Live data is here | Values should match expected engine readings | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_003 | DieselGenerator | Verify 'Generator Group' values are displayed correctly | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Check values under 'Generator Group' | User can see the Live data is here | Values should match expected generator readings | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_004 | DieselGenerator | Check if 'Event Time' is displayed for all parameters | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Ensure all rows have an event time | User can see the Live data is here | Each row should have a valid timestamp | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_005 | DieselGenerator | Verify the 'Status' indicators are correctly displayed | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Check the status indicators next to each parameter | User can see the Live data is here | Indicators should accurately reflect system state | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_006 | DieselGenerator | Validate TRAP alert is triggered correctly | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Check if 'TRAP (S) Received' appears when a trap is received | User can see the Live data is here | Alert should appear when a TRAP event occurs | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_007 | DieselGenerator | Validate Critical Trap alert is triggered correctly | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Check if 'Critical Trap (S) Received' appears when a critical trap is received | User can see the Live data is here | Alert should appear when a critical event occurs | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_008 | DieselGenerator | Ensure UI layout is correctly aligned | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Verify tables and sections are properly formatted | User can see the Live data is here | UI should be properly aligned without overlapping | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_009 | DieselGenerator | Check if application updates values in real-time | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Monitor the values and ensure they update as expected | User can see the Live data is here | Values should refresh periodically | Generator data can view successfully | Pass | Test executed successfully without any issues
DG_010 | DieselGenerator | Verify voltage and current values are within expected ranges | Srikanth | 2025-09-17 | NA | Data get from Manager Application. | Compare displayed values with acceptable ranges | User can see the Live data is here | Values should be within expected operational limits | Generator data can view successfully | Pass | Test executed successfully without any issues

## UPS
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
UPS_001 | UPS | Verify 'UPS Identity Parameters' are displayed correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check values under 'UPS Identity Parameters' | User can see the Live data is here | Values should match expected UPS details | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_002 | UPS | Verify 'UPS Input Parameters' are displayed correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check values under 'UPS Input Parameters' | User can see the Live data is here | Values should match expected UPS readings | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_003 | UPS | Verify 'UPS Output Parameters' are displayed correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check values under 'UPS Output Parameters' | User can see the Live data is here | Values should match expected UPS readings | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_004 | UPS | Verify 'UPS Bypass Parameters' are displayed correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check values under 'UPS Bypass Parameters' | User can see the Live data is here | Values should match expected UPS readings | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_005 | UPS | Check if 'Event Time' is displayed for all parameters | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Ensure all rows have an event time | User can see the Live data is here | Each row should have a valid timestamp | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_006 | UPS | Verify the 'Status' indicators are correctly displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check the status indicators next to each parameter | User can see the Live data is here | Indicators should accurately reflect system state | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_007 | UPS | Validate TRAP alert is triggered correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check if 'TRAP (S) Received' appears when a trap is received | User can see the Live data is here | Alert should appear when a TRAP event occurs | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_008 | UPS | Validate Critical Trap alert is triggered correctly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check if 'Critical Trap (S) Received' appears when a critical trap is received | User can see the Live data is here | Alert should appear when a critical event occurs | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_009 | UPS | Ensure UI layout is correctly aligned | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Verify tables and sections are properly formatted | User can see the Live data is here | UI should be properly aligned without overlapping | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_010 | UPS | Check if application updates values in real-time | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Monitor the values and ensure they update as expected | User can see the Live data is here | Values should refresh periodically | UPS data can view successfully | Pass | Test executed successfully without any issues
UPS_011 | UPS | Verify voltage and current values are within expected ranges | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Compare displayed values with acceptable ranges | User can see the Live data is here | Values should be within expected operational limits | UPS data can view successfully | Pass | Test executed successfully without any issues

## Switch
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
Switch_001 | Switch | Verify that all switch parameters are displayed correctly | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All switch ports should be listed with status | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_002 | Switch | Verify that Admin Parameters are loaded correctly | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All Admin Status entries should be displayed | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_003 | Switch | Verify that Operation Parameters are displayed | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All Operation Status entries should be listed | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_004 | Switch | Verify that Cisco Environment Temperature parameters are displayed | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All temperature-related parameters should be listed | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_005 | Switch | Check if status indicators are updating dynamically | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Status indicators should change based on real-time data | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_006 | Switch | Check if tooltips/icons for Admin/Operation parameters work | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Icons should provide expected tooltips or actions | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_007 | Switch | Verify UI responsiveness | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | UI elements should adjust correctly on resizing | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_008 | Switch | Ensure event timestamps appear correctly | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All Event Time fields should show valid timestamps | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_009 | Switch | Check if scrollbar appears when needed | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Scrollbar should appear if data exceeds visible area | Switch data can view successfully | Pass | Test executed successfully without any issues
Switch_010 | Switch | Verify error handling in the Switch if sub system slide to next page | Srikanth | 2025-09-19 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | UI should handle missing or incorrect data gracefully | Switch data can view successfully | Pass | Test executed successfully without any issues

## Radio
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
Radio_001 | Radio | Verify that Terminal Mode options (Base, Remote, Repeater) are displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All three options should be visible | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_002 | Radio | Verify that IP Address fields (ManagerIpAddress, NetMaskIpAddress) are displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Both fields should be visible | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_003 | Radio | Verify that Voltage parameters are displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All voltage values (+5V, +12V, -5V, +49V) should be visible | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_004 | Radio | Verify that Slot Information section displays all slots | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All slots (1-6) should be listed | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_005 | Radio | Verify that Slot Active indicators are working | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Slot Active status should reflect real-time data | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_006 | Radio | Verify that Link, Channel No, RSSI, SNR, and other parameters are displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | All parameters should have correct values | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_007 | Radio | Verify that TRAP (S) Receive section is displayed | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | TRAP (S) Receive should be visible and updated dynamically | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_008 | Radio | Verify that UI elements are aligned properly | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | UI should not have overlapping or misaligned elements | Radio data can view successfully | Pass | Test executed successfully without any issues
Radio_009 | Radio | Check if the status indicators change dynamically | Srikanth | 2025-09-18 | NA | Data get from Manager Application. | Check all parameters correctly. | User can see the Live data is here | Status indicators should reflect real-time changes | Radio data can view successfully | Pass | Test executed successfully without any issues

## Configuration Test Case (hidden)
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
Config_001 | Configuration | Verify UI layout and elements | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@123 | The corresponding parameter list should load correctly for each subsystem | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_002 | Configuration | Verify subsystem selection | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@124 | The fields should become editable | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_003 | Configuration | Verify Edit button functionality | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@125 | The latest data should be loaded from the backend | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_004 | Configuration | Verify Refresh button functionality | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@126 | All columns should be correctly populated with data | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_005 | Configuration | Verify column data population | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@127 | The updated values should be stored correctly | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_006 | Configuration | Verify Min and Max values update | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@128 | The UI should highlight values based on the configured range | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_007 | Configuration | Verify range color classification | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@129 | The user should be logged out and redirected to the login screen | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_008 | Configuration | Verify logout functionality | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@130 | A help dialog or document should open | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_009 | Configuration | Verify Help button functionality | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@131 | The table should scroll smoothly without UI glitches | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_010 | Configuration | Verify scrollbar functionality | Srikanth | 2025-09-17 | NA | Configuration data takes from configuration text file | User wants to click login | Username: Icomm Password: Icomm@132 | The table should scroll smoothly without UI glitches | Configuration View Successfully. | Pass | Test executed successfully without any issues
Config_011 | Configuration | Verify Normal User Login | Srikanth | 2025-09-17 | NA | NA | User wants to click login | Username: Icomm Password: Icomm@133 | If User is a Normal user he don't have access to edit the data. | NA | Pass | Test executed successfully without any issues

## DashBoard
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
UI_01 | DashBoard | Verify that the dashboard layout is displayed correctly. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | All UI elements should be properly aligned and visible. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_02 | DashBoard | Verify that the current date and time are displayed correctly. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@124 | Date and time should be accurate and update dynamically. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_03 | DashBoard | Verify that the 'Logout' button is visible and functional. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Clicking 'Logout' should log the user out and return to the login screen. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_04 | DashBoard | Verify that the 'Sub Systems Info' tab is displayed and accessible. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The tab should be clickable and open the respective panel. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_05 | DashBoard | Verify that the 'Mains Parameters' table displays correct values. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The values should match the backend data source. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_06 | DashBoard | Verify that the 'UPS Parameters' table displays correct values. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The values should be retrieved and displayed accurately. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_07 | DashBoard | Verify that the 'Event Time' column displays correct timestamps. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Timestamps should be formatted correctly and accurate. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_08 | DashBoard | Verify that the status indicators are displayed correctly for each parameter. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Status should match the corresponding system state. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_09 | DashBoard | Verify that the 'TRAP (S) Received' section updates when a new trap is received. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The trap count should increase dynamically. | Dashboard View succesfully | Pass | Test executed successfully without any issues
UI_10 | DashBoard | Verify that clicking the navigation arrows moves between subsystems. | Srikanth | 2025-09-16 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The subsystem panels should change accordingly. | Dashboard View succesfully | Pass | Test executed successfully without any issues

## Tabular Report
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
TR_001 | TableReports | Launch the application and check the default 'From Date' and 'To Date' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Dates should be pre-filled with the current date | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_002 | TableReports | Select a different 'From Date' and 'To Date' and click 'Filter' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Report should display data for the selected date range | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_003 | TableReports | Toggle between 'SNMP Trap' and 'SNMP Non Trap' and click 'Filter' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Report should update according to the selected SNMP type | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_004 | TableReports | Compare the displayed data with the expected system logs | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Report data should match expected values | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_005 | TableReports | Navigate through report pages using pagination controls | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | User should be able to navigate through pages correctly | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_006 | TableReports | Use the search bar to find a specific parameter | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | The searched parameter should be highlighted or displayed | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_007 | TableReports | Resize the window or use different screen resolutions | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | UI should remain properly aligned and functional | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_008 | TableReports | Click on the 'Close' button | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Application should close or return to the previous screen | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues
TR_009 | TableReports | Check the format of the event time in the report | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Time should be in 'DD-MM-YYYY HH:MM' format | Table Reports Viewed Successfully. | Pass | Test executed successfully without any issues

## LineGraph
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
LG_001 | Linegraph | Launch the application and check default 'From Date' and 'To Date' | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Dates should be pre-filled with the current date | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_002 | Linegraph | Select different 'From Date' and 'To Date', then click 'Load Graph' | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should display data for the selected date range | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_003 | Linegraph | Choose a different parameter from the dropdown and click 'Load Graph' | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should update according to the selected parameter | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_004 | Linegraph | Check the plotted graph values against the expected data | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should accurately represent the parameter values | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_005 | Linegraph | Resize window or use different screen resolutions | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should adjust without misalignment or distortion | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_006 | Linegraph | Select parameters and Click 'Load Graph' after selecting parameters and date | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should update based on the selected inputs | Linegraph Viewed Successfully. | Pass | After Clickload button not reflecting.
LG_007 | Linegraph | Select a date range with no data and click 'Load Graph' | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Graph should display an appropriate message instead of an empty screen | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_008 | Linegraph | Check X-axis and Y-axis labels for correctness | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Labels should correspond to 'Date Time' and 'Parameter Value' | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_009 | Linegraph | Click the 'Logout' button | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | User should be logged out and redirected to the login page | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues
LG_010 | Linegraph | Click the 'Help' button | Srikanth | 2025-09-18 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Help documentation should be displayed | Linegraph Viewed Successfully. | Pass | Test executed successfully without any issues

## Archive Management
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
MA_001 | ManageArchive | Launch the application and check default 'From Date' and 'To Date' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Dates should be pre-filled with the current date | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_002 | ManageArchive | Select different 'From Date' and 'To Date', then click 'View' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Records should be displayed for the selected date range | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_003 | ManageArchive | Toggle between 'SNMP Trap' and 'SNMP Non Trap' and click 'View' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Records should update according to the selected SNMP type | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_004 | ManageArchive | Click 'Next' and 'Previous' buttons | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | User should be able to navigate between pages correctly | Manage Archive Viewed Successfully | Pass | Preview is not working (No Data Found Error Msg)
MA_005 | ManageArchive | Check displayed records against the expected system logs | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Displayed data should match expected values | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_006 | ManageArchive | Modify a record and click 'Save' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Changes should be successfully saved | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_007 | ManageArchive | Select a record and click 'Delete' | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Selected record should be removed from the list | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_008 | ManageArchive | Click 'View' after selecting filter criteria | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Relevant records should be displayed | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_009 | ManageArchive | Resize window or use different screen resolutions | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Table and buttons should remain properly aligned | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues
MA_010 | ManageArchive | Click the 'Logout' button | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | User should be logged out and redirected to the login page | Manage Archive Viewed Successfully | Pass | Test executed successfully without any issues

## User Management
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
MU_01 | UserManagement | Click the 'Delete' button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can delete the selected data using this. | Manage User Viewed Successfully | Pass | Test executed successfully without any issues
MU_02 | UserManagement | Click the 'Create User' button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can create new user using this button. | Manage User Viewed Successfully | Pass | Test executed successfully without any issues
MU_03 | UserManagement | With Existing user details to New Creating user | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can create new user using Existing UserDetails. | Manage User Viewed Successfully | Pass | Test executed successfully without any issues.
MU_04 | UserManagement | Miss-Match Password | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin Enter mis-match Password for New User | Verifyed that Error message: Password Do not Match. | Pass | Test executed successfully without any issues
MU_05 | UserManagement | Click on Edit Button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can Edit the Details or data using Edit Button | Verifyed that It is Editable working fine. | Pass | Test executed successfully without any issues
MU_06 | UserManagement | Click on Save Button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can Save the Data using Save Button | Verifyed that Data is saved Succesfully.working fine. | Pass | Test executed successfully without any issues
MU_07 | UserManagement | Click on Cancel Button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin can Close the Add new UserWindow using Cancel Button | Verifyed that Window is Closed Successfully. | Pass | Test executed successfully without any issues
MU_08 | UserManagement | Click on Logout Button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin Can Logout the Application using logout Button. | Verifyed that Application Closed successfully | Pass | Test executed successfully without any issues
MU_09 | UserManagement | UserManagement Window Alinement,Timer and logs | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin Open Usermanagement window Alinement show data Formate and Time | Verifyed that alignment, data format, and time are displayed correctly. | Pass | Test executed successfully without any issues
MU_10 | UserManagement | Click on Show and Hide Icon | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin Click on Show-Hide Icon visible the password default it is Hide.(Dots) | Verifyed that Show Hide Icon working fine. | Pass | Test executed successfully without any issues
MU_11 | UserManagement | Click on Create button | Srikanth | 2025-09-20 | NA | User can login with the right credentials | User wants to click login | Username: Icomm Password: Icomm@123 | Admin Try to Create new user Click on the Create button in the AddUserWindow. | Create the user successfully | Pass | Error message: UserName or Password or Mail Already exicuted.

## Sub-SystemStatus
Test Case ID | Sub-System | Test Description | Tester Name | Execution Date | Preconditions | Dependencies | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments/Notes
SI-001 | Subsysteminfo | Verify that the Sub System Status window loads correctly | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The window should display without errors | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-002 | Subsysteminfo | Check that all sections and panels are visible | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | All panels should be displayed properly | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-003 | Subsysteminfo | Validate that the Preview Mode toggle button is displayed in each section | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Preview Mode should be visible in all panels | Subsysteminfo data viewd. | Pass | There is no preview button in the Window.
SI-004 | Subsysteminfo | Ensure that the icons and colors for status indicators are correctly displayed | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Icons should be visible and should represent statuses correctly | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-005 | Subsysteminfo | Test resizing the window and ensure all UI elements adjust properly | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The UI should be responsive without overlapping or breaking layout | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-006 | Subsysteminfo | Verify that Mains Frequency, Voltage values, Status, and Event Time are correctly displayed | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The values should be accurate and formatted correctly | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-007 | Subsysteminfo | Ensure that Status indicators (dots) reflect actual system status | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The status should change dynamically based on real-time values | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-008 | Subsysteminfo | Test whether scrolling works if additional data is present | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The user should be able to scroll smoothly | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-009 | Subsysteminfo | Verify that Battery Status, Manufacturer, Model, Software Version, and Serial Number are displayed | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Correct details should be visible | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-010 | Subsysteminfo | Ensure Event Time updates correctly when new data arrives | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The event time should reflect the latest updates | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-011 | Subsysteminfo | Validate that Battery Status shows correct values (e.g., 'batteryDepleted') | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The status should be accurate | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-012 | Subsysteminfo | Verify that each port's status (GE/10/1, GE/0/0, etc.) is displayed | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | All ports should be listed with their correct status | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-013 | Subsysteminfo | Check that the router admin status section displays proper event time and link status | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Information should be correct and up to date | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-014 | Subsysteminfo | Ensure that the status indicators (dots) correctly reflect active/inactive states | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Green for active, grey for inactive (or per defined color coding) | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-015 | Subsysteminfo | Verify that the Terminal Mode radio buttons work correctly | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Selecting a mode should update the system accordingly | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-016 | Subsysteminfo | Check that IP Address fields (Manager IP, Netmask IP) accept and display valid data | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Fields should accept only valid IP formats | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-017 | Subsysteminfo | Verify that Voltage parameter is displayed correctly | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The value should be accurate | Subsysteminfo data viewd. | Pass | Test executed successfully without any issues
SI-018 | Subsysteminfo | Ensure the voltage indicator updates dynamically when values change | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The indicator should refresh without lag | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-019 | Subsysteminfo | Verify that Trap ID, System Name, Trap Info, Trap Group Name, and Trap Value are displayed properly | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Data should be formatted correctly | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-020 | Subsysteminfo | Test sorting functionality for Trap ID and other columns | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Sorting should work as expected | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-021 | Subsysteminfo | Ensure that scrolling works smoothly when multiple trap logs are displayed | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The user should be able to scroll without lag | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-022 | Subsysteminfo | Verify that the dashboard updates data in real-time | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | Data should refresh dynamically | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-023 | Subsysteminfo | Test the Detail Mode toggle button to selected sub-system screen should be appear | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The mode should switch as expected | Subsysteminfo data viewed. | Pass | It is All Ways Enable mode only.
SI-024 | Subsysteminfo | Check application performance with a large number of data entries | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The application should not lag or crash | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-025 | Subsysteminfo | Verify behavior when no data is available | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | UI should display 'No Data Available' instead of crashing | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues
SI-026 | Subsysteminfo | Check how the system voltage or status data in dg | Srikanth | 2025-09-19 | NA | User can login with the right credentials | User wants to click the subsysteminfo button. | Username: Icomm Password: Icomm@123 | The UI should show an appropriate error message | Subsysteminfo data viewed. | Pass | Test executed successfully without any issues